{"text_format":"2","workbook":"xlsx","n_sheets":2,"sheets":["任务_表1","Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"任务_表1","index":0,"n_rows":7,"n_cols":6,"rows_kept":7,"cut":false,"hidden":false,"merged":[]}
["名称","工期","开始时间","完成时间","参与人","提交成果"]
["需求","14 个工作日","2019-01-07","2019-01-24","陈龙,邬申涛","需求分析及初步方案"]
["设计","9 个工作日","2019-01-25","2019-02-21","邬申涛,游省吉,周亮","系统详细设计"]
["后台开发","30 个工作日","2019-02-22","2019-04-04","邬申涛,游省吉","后台系统开发及单元测试完成"]
["前台开发","40 个工作日","2019-02-22","2019-04-18","陈龙,周亮","前台开发及单元测试完成"]
["集成测试","7 个工作日","2019-04-18","2019-04-29","陈龙,邬申涛","系统压力测试及试运行"]
["实施","7 个工作日","2019-04-22","2019-05-01","陈龙,邬申涛","系统上线"]

{"sheet":"Sheet1","index":1,"n_rows":6,"n_cols":5,"rows_kept":6,"cut":false,"hidden":false,"merged":[]}
["开始时间","完成时间"]
["2019-02-22","2019-04-18"]
["2019-04-18","2019-04-29",null,"开始时间","完成时间"]
["2019-04-22","2019-05-01",null,"2019-01-07","2019-01-24"]
[null,null,null,"2019-01-25","2019-02-21"]
[null,null,null,"2019-02-22","2019-04-04"]