{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":45,"n_cols":5,"rows_kept":45,"merged":[[6,1,6,4],[12,1,12,4],[18,1,18,4],[25,1,25,4]],"flags":["formulas_cached_only"]}
[]
[null,"序号","日期星期","计划内容","完成内容"]
[null,1,"20160510、星期二",null,"早上公司开项目会议、下们准备星期二金虎开项目启动会议资料"]
[null,2,"20160511、星期三",null,"上午金虎项目启动会，公司项目前期开发准备及后台系统管理功能"]
[null,3,"20160512、星期四",null,"WebApi资源管理、员工档案、业务单位、组织机构"]
[null,4,"20160513、星期五",null,"业务单位成员、修改密码、重置密码"]
[]
[null,5,"20160516、星期一","专买店档案、专买店业务员、专买点收货地址","专买店档案、专买店业务员、专买点收货地址"]
[null,6,"20160517、星期二","区域档案、存货档案、存货分类、","区域档案、存货档案、存货分类"]
[null,7,"20160518、星期三","存货资源、组合商品","存货资源、组合商品组成套件、计量单位"]
[null,8,"20160519、星期四","系统登录、动态系统菜单、产品标记图片","系统登录、动态系统菜单、产品标记图片"]
[null,9,"20160520、星期五","功能权限、订单计价","功能权限"]
[]
[null,10,"20160523、星期一","接口日志、接口队列、活动记录","订单审核、资源管理WebApi发布问题"]
[null,11,"20160524、星期二","金虎展示现完成功能","订单审核、接品队列、接品日志"]
[null,12,"20160525、星期三","系统参数、投诉记录、商品反馈意见","金虎公司展示功能并讨论"]
[null,13,"20160526、星期四",null,"发布程序在160服务品上、修改问题功能"]
[null,14,"20160527、星期五","组合参数类别、组合参数","组合参数类别、组合参数"]
[]
[null,15,"20160530、星期一","组合商品定义、组合商品定义参数、组合商品定义组成套件","组合产品、活动管理"]
[null,16,"20160531、星期二","定制产品","定制产品、组合产品"]
[null,17,"20160601、星期三",null,"活动管理"]
[null,18,"20160602、星期四",null,"订单审核"]
[null,19,"20160603、星期五",null,"投诉管理、功能测试"]
[null,20,"20160604、星期六",null,"功能测试"]
[]
[null,20,"20160606、星期一","功能测试"]
[null,21,"20160607、星期二","金虎会议"]
[null,22,"20160608、星期三"]
[null,23]
[null,24]
[null,25]
[null,26]
[null,27]
[null,28]
[null,29]
[null,30]
[null,31]
[null,32]
[null,33]
[null,34]
[null,35]
[null,36]
[null,37]
[null,38]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}