{"text_format":"3","workbook":"xls","n_sheets":7,"sheets":["整体实施计划","详细计划与实施情况0620-0624","详细计划与实施情况0613-0617","详细计划与实施情况0530-0603","详细计划与实施情况0523-0527","详细计划与实施情况0516-0520","详细计划与实施情况0509-0513"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"整体实施计划","index":0,"n_rows":8,"n_cols":6,"rows_kept":8,"flags":["formulas_cached_only"]}
["计划"]
["开始时间","结束时间","内容","成果","预计参与人员","是否完成"]
["2016-05-09","2016-05-16","客户方需求调研，项目架构搭建","需求设计说明书","邬申涛、刘开航、淳老师"]
["2016-05-17","2016-06-10","开发完成：订购系统前后台；U8接口","系统软件","邬申涛、刘开航、淳老师、陈龙"]
["2016-06-13","2016-06-24","系统单元测试，以及调整","系统软件","邬申涛、刘开航"]
["2016-06-27","2016-07-01","演示版本系统","系统软件","邬申涛、刘开航"]
["2016-07-01","2016-07-07","系统数据初始化","系统数据","邬申涛、刘开航"]
["2016-07-11",null,"系统试运行","系统运行报告","邬申涛、刘开航"]

{"sheet":"详细计划与实施情况0620-0624","index":1,"n_rows":10,"n_cols":8,"rows_kept":10,"merged":[[1,0,3,0],[1,1,3,1],[5,0,7,0],[5,1,7,1],[8,0,10,0],[8,1,10,1]],"flags":["formulas_cached_only"]}
["开始时间","结束时间","内容","成果","主要责任人","完成情况评估","问题","建议"]
["2016-06-20","2016-06-24","单据导入U8，以及从U8系统获取发货数据测试","成功生成U8销售订单，并在U8系统中走完所有流程后，获取发货数据","邬申涛"]
[null,null,"订购系统细节性修改",null,"刘开航"]
[null,null,"订购系统细节性修改",null,"陈龙"]
["2016-06-20","2016-06-20","单据导入U8，以及从U8系统获取发货数据测试","成功生成U8销售订单，并在U8系统中走完所有流程后，获取发货数据","邬申涛"]
["2016-06-21","2016-06-21"]
[null,null,"启动与金虎公司共同开始测试及培训订购系统",null,"刘开航"]
[]
["2016-06-24","2016-06-24"]
[null,null,"完成订购系统使用视频录制","订购系统使用视频","刘开航"]

{"sheet":"详细计划与实施情况0613-0617","index":2,"n_rows":8,"n_cols":8,"rows_kept":8,"merged":[[1,0,3,0],[1,1,3,1],[4,0,6,0],[4,1,6,1],[7,0,9,0],[7,1,9,1]],"flags":["formulas_cached_only"]}
["开始时间","结束时间","内容","成果","主要责任人","完成情况评估","问题","建议"]
["2016-06-13","2016-06-17"]
[null,null,"订购系统细节性修改",null,"刘开航","完成"]
[null,null,"根据测试文档修改其中问题",null,"陈龙"]
["2016-06-15","2016-06-15","在金虎公司部署测试环境（数据库、接口部分），处理基础资料数据","环境部署完成、U8基础数据导入完成","邬申涛","完成"]
[null,null,"在金虎公司部署测试环境（BS部分）","BS环境部署完成","刘开航","完成"]
[null,null,"根据测试文档修改其中问题",null,"陈龙","完成"]
["2016-06-16","2016-06-16","批量处理金虎公司订购系统基础数据（产品分类、组合等）","基础数据批量处理完成，达到运行标准","邬申涛","完成"]

{"sheet":"详细计划与实施情况0530-0603","index":3,"n_rows":14,"n_cols":8,"rows_kept":14,"merged":[[1,0,3,0],[1,1,3,1],[4,0,5,0],[4,1,5,1],[6,0,8,0],[6,1,8,1],[9,0,11,0],[9,1,11,1],[12,0,13,0],[12,1,13,1]],"flags":["formulas_cached_only"]}
["开始时间","结束时间","内容","成果","主要责任人","完成情况评估","问题","建议"]
["2016-05-30","2016-05-30"]
[null,null,"组合商品定义、组合商品定义参数、组合商品定义组成套件",null,"刘开航"]
[null,null,"修改产品中心",null,"陈龙"]
["2016-05-31","2016-05-31","定制产品",null,"刘开航"]
[null,null,"修改产品中心",null,"陈龙"]
["2016-06-01","2016-06-01"]
[null,null,"开发获取U8信用",null,"刘开航"]
[null,null,"修改产品详细页",null,"陈龙"]
["2016-06-02","2016-06-02"]
[null,null,"开发获取U8价格",null,"刘开航"]
[null,null,"修改收藏夹",null,"陈龙"]
["2016-06-03","2016-06-03",null,null,"刘开航"]
[null,null,"制作账户中心",null,"陈龙"]

{"sheet":"详细计划与实施情况0523-0527","index":4,"n_rows":15,"n_cols":8,"rows_kept":15,"merged":[[1,0,3,0],[1,1,3,1],[5,0,7,0],[5,1,7,1],[8,0,10,0],[8,1,10,1],[11,0,12,0],[11,1,12,1],[13,0,15,0],[13,1,15,1]],"flags":["formulas_cached_only"]}
["开始时间","结束时间","内容","成果","主要责任人","完成情况评估","问题","建议"]
["2016-05-23","2016-05-23","开发销售订单导入U8功能",null,"邬申涛"]
[null,null,"完成开发接口日志、接口队列、活动记录","接口日志、接口队列、活动记录","刘开航","完成"]
[null,null,"产品详细页面开发","产品详细页面","陈龙","完成"]
["2016-05-24T09:00:00","2016-05-24T12:00:00","金虎展示现完成功能",null,"邬申涛、刘开航、陈龙","完成"]
["2016-05-24","2016-05-24","完成并测试销售订单导入U8功能","销售订单导入U8功能","邬申涛","完成"]
[null,null,"根据客户对展示功能提出的意见进行调整",null,"刘开航"]
[null,null,"首页页面开发","首页页面","陈龙","完成"]
["2016-05-25","2016-05-25"]
[null,null,"开发完成系统参数、投诉记录、商品反馈意见","系统参数、投诉记录、商品反馈意见功能模块","刘开航","次要功能后续完成"]
[null,null,"账户中心页面开发","账户中心页面","陈龙","完成"]
["2016-05-26","2016-05-26","WebServers客户信用获取功能的开发",null,"刘开航，邬申涛"]
[null,null,"根据客户对展示功能提出的意见进行调整",null,"陈龙"]
["2016-05-27","2016-05-27","完成WebServers客户信用获取功能的开发","获取客户信用","刘开航"]
[null,null,"问卷调查页面开发",null,"陈龙"]

{"sheet":"详细计划与实施情况0516-0520","index":5,"n_rows":15,"n_cols":8,"rows_kept":15,"merged":[[2,0,3,0],[2,1,3,1],[4,0,6,0],[4,1,6,1],[7,0,9,0],[7,1,9,1],[10,0,11,0],[10,1,11,1],[12,0,14,0],[12,1,14,1]],"flags":["formulas_cached_only"]}
["开始时间","结束时间","内容","成果","主要责任人","完成情况评估","问题","建议"]
["2016-05-16T09:00:00","2016-05-16T11:00:00","与金虎家私沟通组合产品实现方式","完善需求设计说明书","邬申涛","完成"]
["2016-05-16","2016-05-16","完成专买店档案、专买店业务员、专买点收货地址开发",null,"刘开航","完成"]
[null,null,"完成订单中心前台页面开发","订单中心前台页面","陈龙","完成"]
["2016-05-17","2016-05-17","开发U8客户档案、产品档案自动同步",null,"邬申涛","完成"]
[null,null,"完成区域档案、存货档案、存货分类的开发",null,"刘开航","完成"]
[null,null,"开发产品中心页面",null,"陈龙"]
["2016-05-18","2016-05-18","完成U8客户档案、产品档案自动同步的开发，并交付测试","接口程序","邬申涛","完成"]
[null,null,"完成存货资源、组合商品开发",null,"刘开航","完成"]
[null,null,"开发产品中心页面",null,"陈龙"]
["2016-05-19","2016-05-19","测试已经完成的系统管理、业务单位成员、区域档案、存货档案、存货分类、存货资源、组合商品开发功能","系统管理、业务单位成员、区域档案、存货档案、存货分类、存货资源、组合商品功能","刘开航","完成",null,"同时完成系统登录、动态系统菜单、产品标记图片"]
[null,null,"完成开发产品中心页面","产品中心页面","陈龙","完成"]
["2016-05-20","2016-05-20","开发订单审核（核价）功能",null,"刘开航",null,null,"已完成功能权限"]
[null,null,"完成收藏夹页面开发","收藏夹页面","陈龙","完成"]
[null,null,"测试自动同步程序，开始准备客户档案WebServers的接口开发",null,"邬申涛",null,null,"交由刘凯航开发，准备开发生成U8销售订单"]

{"sheet":"详细计划与实施情况0509-0513","index":6,"n_rows":9,"n_cols":8,"rows_kept":9,"flags":["formulas_cached_only"]}
["开始时间","结束时间","内容","成果","主要责任人","完成情况评估","问题","建议"]
["2016-05-09","2016-05-09","金虎调研现有客户基础资料、料品基础资料、取价方式、信用查询方式、写入单据","系统实施工作计划；系统实施调研情况说明；","邬申涛","已经完成"]
[null,null,"与客户交流后初步设计前台主要页面，便于后期交流","前台主要页面结构图","刘凯航","已经完成"]
["2016-05-10","2016-05-10","通过调研情况，协助与淳老师进行系统架构搭建",null,null,"已经完成"]
[null,null,"通过调研情况，将会遇到的问题，向淳老师进行描述，共同解决",null,"邬申涛、刘凯航、淳老师","已经完成"]
["2016-05-11","2016-05-11","参与客户项目启动会",null,"邬申涛、刘凯航、淳老师","已经完成"]
[null,null,"再次向客户提出项目实施过程中遇到的问题、给出解决方案",null,"邬申涛、刘凯航、淳老师","已经完成",null,"已经完成WebApi资源管理、员工档案、业务单位、组织机构开发"]
["2016-05-12","2016-05-13","编写需求设计说明书","需求设计说明书；实施过程中可能遇到问题列表","邬申涛、刘凯航","已经完成（文档名：金虎家私经销商订购系统设计实施方案）",null,"已经完成业务单位成员、修改密码、重置密码开发"]
[null,null,"淳老师搭建好系统架构","系统架构","淳老师","已经完成",null,"陈龙完成购物车功能"]